SavePlate — Smart Food Waste Reduction Application

Work Breakdown Structure (WBS)

BIT216 Software Engineering Principles — Task 1 (30 May – 12 June 2026)

The work breakdown structure below divides Task 1 into five phases. Each phase is broken down into smaller tasks. Every task has a member responsible for it, a start and end date, and a deliverable. Saturdays are kept as non-working days.

| Member | Role |
| --- | --- |
| Shekhar Bhatt | Project Manager |
| Manish Bhatta | Developer |
| Nikhil Tamrakar | Designer |

| ID | Task | Owner | Start | End | Deliverable |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Research and Drafting | All | 30 May | 2 Jun | Sections 1–4 drafted |
| 1.1 | Research Nepali food waste data | All | 30 May | 31 May | Reference list |
| 1.2 | Draft Section 1 — Overview | Shekhar | 1 Jun | 2 Jun | Overview section |
| 1.3 | Draft Sections 2–3 — Aims and Objectives | Manish | 1 Jun | 3 Jun | Aims and objectives |
| 1.4 | Draft Section 4 — Scope | Nikhil | 1 Jun | 3 Jun | Scope section |
| 2.0 | Schedule Development | Shekhar | 4 Jun | 8 Jun | Section 5 complete |
| 2.1 | Develop WBS table | Shekhar | 4 Jun | 5 Jun | WBS table |
| 2.2 | Build and export Gantt chart | Shekhar | 7 Jun | 8 Jun | Gantt chart image |
| 2.3 | Milestones table | Manish | 4 Jun | 5 Jun | Milestones table |
| 3.0 | Technical Description | All | 4 Jun | 8 Jun | Section 6 complete |
| 3.1 | Development tools table (6.1) | Manish | 7 Jun | 8 Jun | Tools table |
| 3.2 | Hardware table (6.2) | Nikhil | 4 Jun | 5 Jun | Hardware table |
| 3.3 | Demonstration table (6.3) | Nikhil | 7 Jun | 7 Jun | Demo table |
| 4.0 | Risk Management | All | 8 Jun | 9 Jun | Section 7 complete |
| 4.1 | Risk brainstorm session | All | 8 Jun | 8 Jun | Risk list |
| 4.2 | Risk rows 1–3 | Shekhar | 9 Jun | 9 Jun | Three risks |
| 4.3 | Risk rows 4–5 | Manish | 9 Jun | 9 Jun | Two risks |
| 4.4 | Risk rows 6–7 | Nikhil | 9 Jun | 9 Jun | Two risks |
| 5.0 | Review and Submit | All | 10 Jun | 12 Jun | Final document |
| 5.1 | Peer review and formatting | All | 10 Jun | 10 Jun | Reviewed draft |
| 5.2 | Insert Gantt, final commit | Shekhar | 11 Jun | 11 Jun | Final document |
| 5.3 | Submit to Turnitin | All | 12 Jun | 12 Jun | Submitted |

Note: Rows ending in .0 are the main phases; the numbered tasks beneath each one are the work packages. All deliverables are saved to the project GitHub repository.